## Overview
# | Component | Description | Priority
1 | Synapse lite BE
2 | Synapse lite MA
3 | Synapse lite FE
4 | Apex lite BE
5 | Apex lite FE

## Features
Synapse Lite |  | Apex Lite | Apex Lite : Vendor Interface
Define the Plans (CapEx, OpEx)
Define the Pricing for the devices (VT, CT, PT) and Plans
Define the Device Configuration Details (MQTT Topics, Input, Output Payload)
Define the vendors (Create, Update, Activate, Deactivate)
Configure the order route based on location of vendors
Download & Install Synapse Lite Mobile App
Consumer Registration
Consumer Login to Mobile, Web App
Purchase Devices
Payment completion
Order submission to corresponding vendor (Configs, Tag- Ids, Consumer Details) Primary or Secondary Vendor
|  | Send Order Notifications (Email,SMS,WhatsApp) to Vendor | Vendor Accepts the Order & Acknowledge
|  | In case of vendor not accepted the Order - Route the Order to a different vendor | Update the Order with target date of completion
Receive the Order confirmation info with target date of completion
Update the Order with Delivery info with tracking info
Receive the Order Shipment info with Delivery & Tracking info
Consumer acknowledge the Order on receiving (No Extra Step needed) | No Extra Step needed
Consumer reports the return order for the damaged Tags. Return option should be disable after certain period of time
Consumer Activates the Tags |  | Validates the Tags while activation
Synapse Lite BE should be ready to receive the Tag Data
Consumer need to map the Tag to Entity (Vehicle, Asset, Child, Pet)
Tag need to send the Diagnosis Details on a daily basis and on request
Need to receive the Tag Diagnosis Details on a Daily basis and On Request also from Tag to Synapse Lite BE
SLBE should be capable of generate the timeline / travel history of the tag
SLBE should be capable of receiving the Critical Alerts from the Tags and display in Consumer interface (Web App, Mobile App)
SLBE should be capable of generating the Reports and display in Consumer interface (Web App, Mobile App)
Devices Live Tracking - Site View [Live Map]
Notifications : In App, SMS, Email, WhatsApp

## Q & A
# | Question | Answer
1 | Non Tracklynk Tags are not allowed in Tracklynk lite application ? | Yes
2 | Tag Ids will be generated in Apex and provided to Vendor to configure in the Tags | Yes
3 | Are we going to handle the warranty of the Tags scenario in Apex ? if not how ? | We TLL need to handle it | TBD
4 | Need to define the Damaged Tags return policy. Return to Apex or to Vendor ? |  | TBD
5 | Need to define the FOTA flow
6 | Need to define the MQTT Topics for all the Events L -> R and R -> L | Need to define with Standard
7 | Do we need to have the prediction mechanism | Yes
8 | Are we having the collision detection feature | Yes
9 | Does Tag contains any LED light or Buzzer ? | Only LED
10 | How does the Tag configuration will be updated ? | Should be in the mobile App
11 | For PT and CT are we having the Body Vitals ? | No
12 | Does the CT contains SoS ? | No

## Sheet1
# | Screen | Feature | Bouncie | Version | UX (Shobhit) | Frontend Web | Frontend Native | Backend | Priority | Phase | Notes / Gap Analysis
HOME / MAP
1 | Home / Map | Vehicle pin on live map | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Map renders via Google Maps. Pin exists. No live GPS data — mock coordinates only.
2 | Home / Map | Live GPS refresh (15-second via 4G LTE-M) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | No polling or WebSocket. Map is static after load. Critical for core value prop.
3 | Home / Map | Parked status chip + last engine-off timestamp | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | "Parked" status text shown. Hardcoded. Needs real engine-off event from API.
4 | Home / Map | Current parked address (reverse-geocoded) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Address text shown on Home.jsx. Hardcoded placeholder string.
5 | Home / Map | NWS severe weather badge on map | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie shows NWS badge prominently on map. Not started. Needs NWS API integration.
6 | Home / Map | Vehicle card (name, model, year) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Card renders with mock "Toyota Tacoma 2024". No real vehicle data from OBD/API.
7 | Home / Map | Fuel % health chip | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Chip exists — hardcoded 65%. Needs real OBD fuel sensor value.
8 | Home / Map | Battery health chip (Good/Bad) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Chip exists — hardcoded "Good". Needs real voltage read from OBD.
9 | Home / Map | Engine status chip (check engine) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Chip exists — hardcoded "Good". Needs real MIL/DTC status from OBD.
10 | Home / Map | Device connection chip (OBD online/offline) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Chip exists — hardcoded "Good". Needs actual device last-seen ping from API.
11 | Home / Map | Vehicle card context menu (Notif / Details / Driving Stats) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie's 3-dot on vehicle card opens: Notification Settings, Vehicle Details, Driving Stats. Tracklynk has no such menu.
12 | Home / Map | Map type toggle (Road / Satellite) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie has Road/Satellite picker in map options panel. Not started in Tracklynk.
13 | Home / Map | Live Traffic overlay | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Google Maps traffic layer is not enabled. One-line change once data pipeline is live.
14 | Home / Map | Speed Legend overlay | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Shows colour key for speed bands on map. Not started.
15 | Home / Map | Geo-Zone Areas overlay on map | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie overlays active geofence circles on map. No geofencing built in Tracklynk.
16 | Home / Map | Vehicle pin tap → action sheet (Apple Maps / Google Maps / Uber / Lyft) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Tapping Bouncie's vehicle pin shows action sheet with navigation/ride apps. Nothing in Tracklynk.
17 | Home / Map | Multiple vehicle switcher | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Dropdown UI exists on header. Only 1 mock vehicle. Needs multi-vehicle data model.
18 | Home / Map | Conversational AI assistant (Tracklynk exclusive) | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | EXCLUSIVE TO TRACKLYNK. Expandable bottom sheet with AI quick-actions. UI built, responses are mocked only.
TRIPS LIST
19 | Trips List | Day View — all trips overlaid on single map for the day | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie's second signature feature (v4.15, Sept 2025). Tracklynk shows individual cards. Day View not started.
20 | Trips List | Daily aggregate stats (X trips · Y miles · VIEW DAY button) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie groups trips by day and shows aggregate before you drill in. Tracklynk has no daily summary row.
21 | Trips List | Individual trip rows (start time → end time, distance) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Trips.jsx has 6 mock trip cards. No real trip data. Needs Bouncie /trips API endpoint.
22 | Trips List | Trip list date grouping | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Date grouping structure exists in Trips.jsx with mock dates. Works visually.
23 | Trips List | Trip filter by date range | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Filter sheet UI built with date radio buttons. No real filtering against API data.
24 | Trips List | Trip overflow menu (share, delete, flag) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie has '...' on each trip row. Tracklynk has no per-trip actions.
TRIP DETAIL
25 | Trip Detail | Route replay polyline on map | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | TripDetail.jsx renders polyline via Google Maps. Coordinates are mock arrays. Needs real GPS breadcrumb from API.
26 | Trip Detail | Color-coded speed bands (green/yellow/red vs posted limit) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | CRITICAL GAP. Bouncie's #1 feature. Tracklynk route is single lime color. Need segmented polylines with speed-vs-limit logic.
27 | Trip Detail | Safety / driving score gauge (0–100, A/B/C/D) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | SVG circular gauge built in TripDetail.jsx with color coding. Value is hardcoded mock. Needs real score calculation.
28 | Trip Detail | Hard braking events with timestamp + count | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Event badge exists with icon and mock count. Needs real OBD event data.
29 | Trip Detail | Rapid acceleration events with timestamp + count | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Event badge exists. Mock data only.
30 | Trip Detail | Speed alert events on route | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Event badge exists. Mock data only.
31 | Trip Detail | Trip stats (distance, duration, idle time) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Stats shown in trip detail. All hardcoded. Needs real trip data from API.
32 | Trip Detail | MPG / fuel economy per trip | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | MPG displayed as mock value. Needs real OBD fuel consumption data.
33 | Trip Detail | Max speed for the trip | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie shows max speed on trip. Not displayed in Tracklynk's trip detail screen.
34 | Trip Detail | Start/end address labels on route | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Start (lime) and end (red) markers exist. Labels are hardcoded. Needs real reverse-geocoding.
OBD HEALTH DRILL-DOWN
35 | OBD Health Drill-Down | Fuel detail screen (large dial + notification threshold) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: full screen with fuel % dial, alert threshold config. Tracklynk: chip only, no drill-down at all.
36 | OBD Health Drill-Down | Battery detail screen (voltage value + Normal/Low/Critical thresholds) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie explains 12.6V=Normal, 12V=Low. This IS the battery voltage improvement you identified as a competitive win. Not started.
37 | OBD Health Drill-Down | Engine / DTC codes screen (code + plain-English description) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: "All Good! No trouble codes found" + DTC notification toggle. Tracklynk: no drill-down screen.
38 | OBD Health Drill-Down | Device status screen (IMEI, serial number, last comm timestamp + location) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: shows IMEI, serial, last ping time, last known address. Tracklynk: chip only.
NOTIFICATION CENTER
39 | Notification Center | Drive tab (Hard Braking, Rapid Accel, Curfew, Trip Start/End, Speed) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie's Drive tab is the core alert feed. Zero notification infrastructure in Tracklynk.
40 | Notification Center | Vehicle tab (Impact, Fuel Low, Battery, Geo-fence, DTC, Tamper, Distance, Idle) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | 8 distinct vehicle alert types in Bouncie. None built in Tracklynk.
41 | Notification Center | Care tab (Distance, Idle Time, Trip Fuel Economy, Battery, DTC, Tamper) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Care-specific notification history tab. Not started.
42 | Notification Center | Push notification delivery (FCM / APNs) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Zero push infrastructure. This is the #1 blocker for all alert features. Must be built first.
ALERT CONFIGURATION
43 | Alert Configuration | Hard Braking config (toggle + Excessive / Moderate / Light) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie has 3-level segmented control. Tracklynk has placeholder toggle in Settings — no config screen.
44 | Alert Configuration | Rapid Acceleration config (toggle + 3-level sensitivity) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Same pattern as hard braking. Not started.
45 | Alert Configuration | Speed alert config (Speed Limit + Speed Bands + Excessive MPH threshold) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie has 3 separate speed settings. Not started in Tracklynk.
46 | Alert Configuration | Geo-Zone creation screen (circular zone, name, schedule) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: "Create Geo-Zone" with circular zone builder. Zero geofencing logic in Tracklynk.
47 | Alert Configuration | Curfew creation screen (time window) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: "Create Curfew" with time range. Non-functional toggle in Tracklynk Settings.
48 | Alert Configuration | Trip Start / Trip End config (separate toggles) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie has independent toggles for trip-start and trip-end alerts. Not started.
49 | Alert Configuration | Fuel Level alert slider (threshold %) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: arc slider defaulting to 15%. Not started.
50 | Alert Configuration | Battery alert config (Low & Critical / Critical Only toggle) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie: two-mode battery alert. Not started.
51 | Alert Configuration | Distance Driven alert slider (mile threshold) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: arc slider defaulting to 400 miles. Not started.
52 | Alert Configuration | Idle Time alert config (Start/End + Total options) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: two idle time options. Not started.
53 | Alert Configuration | NWS Weather alert toggle | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: simple push toggle for NWS alerts near vehicle. Not started.
54 | Alert Configuration | Impact Detection + emergency SMS contact | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: toggle + 'Who should receive Accident SMS'. Needs contacts data model + Twilio.
55 | Alert Configuration | DTC / Check Engine push toggle | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: simple push toggle for check engine events. Not started.
56 | Alert Configuration | Tamper Detection toggle (OBD unplugged) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie: fires when adapter removed then reconnected. Not started.
SETTINGS / PROFILE
57 | Settings / Profile | My Profile screen (email, phone, password, Face ID) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | ProfileEditView fully built — first/last name, email, phone, avatar, save with animation. No backend.
58 | Settings / Profile | Delete Account | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | DeleteAccountView fully built — confirmation flow with 2-step verification. No backend wired.
59 | Settings / Profile | Vehicles management (add / edit / remove) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | VehicleDetailView + AddVehicleView both fully built — edit nickname/plate, OBD device card, remove with confirmation flow.
60 | Settings / Profile | Subscription management | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | SubscriptionMain + SwitchPlanView + CancelFlowView all fully built. No Stripe integration.
61 | Settings / Profile | Payment details (billing history, payment method) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | PaymentMethodView fully built — card fields, billing history. No real payment processor.
62 | Settings / Profile | Units setting (Imperial / Metric, MPG / L/100km / km/L) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Not found in Settings.jsx. Bouncie has dedicated Units screen. Not started.
63 | Settings / Profile | App Appearance (Light / Dark / System with visual previews) | ✓ Yes |  | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Not found in Settings.jsx. No in-app theme toggle built.
64 | Settings / Profile | Support / live chat | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | HelpSupportView fully built — FAQ accordion, contact options. No live chat backend.
65 | Settings / Profile | Feedback submission | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Feedback option in HelpSupportView. UI only.
66 | Settings / Profile | Privacy Policy / Terms of Service | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | TermsPrivacyView fully built — tabbed Terms + Privacy with full legal text content.
67 | Settings / Profile | App version display | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Version 1.0.0 shown in WhatsNewView sublabel. Not shown on main settings screen.
—
— | Settings / Profile | Two-Factor Authentication setup flow | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | TwoFactorView fully built — enable/disable 2FA, verification code entry flow. No backend.
— | Settings / Profile | Active Sessions management (view + revoke devices) | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | ActiveSessionsView fully built — lists 3 mock devices with revoke option. No real session data.
— | Settings / Profile | Privacy & Data controls | ✓ Yes |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | PrivacyDataView fully built — data export, analytics toggles. No backend wired.
— | Settings / Profile | What's New / Changelog screen | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | WhatsNewView fully built — versioned changelog. Tracklynk exclusive (Bouncie has no equivalent in-app).
ONBOARDING FLOW | [5 empty] | — | — | — | —
68 | Onboarding Flow | Welcome carousel (hero / features / pricing) | ✗ No |  | ✓ Done | ◑ In Progress | ◑ In Progress | ◑ In Progress | Done | Done | FULLY BUILT. 3-slide carousel with auto-advance, manual swipe, dot navigation.
69 | Onboarding Flow | Auth — Apple / Google OAuth buttons | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | OAuth button UI built. No real authentication backend wired.
70 | Onboarding Flow | Auth — Face ID biometric | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Face ID state machine built in Auth.jsx (idle→scanning→verified). Mock only.
71 | Onboarding Flow | Sign Up (email + password with validation) | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Form built with live validation in SignUp.jsx. No backend account creation.
72 | Onboarding Flow | Add Vehicle — VIN barcode scan | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Scan animation UI built. No camera access or real barcode parsing.
73 | Onboarding Flow | Add Vehicle — manual VIN entry fallback | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Manual input field exists. No VIN validation or vehicle lookup API.
74
75 | Onboarding Flow | OBD device scan + Bluetooth pairing | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Animated scan UI built. No real Bluetooth or device communication.
76 | Onboarding Flow | Device setup wizard (step-through with OBD port illustration) | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Multi-step animation built. No actual device connectivity.
77 | Onboarding Flow | Choose Plan (monthly / annual toggle, animated price) | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Plan selection UI built. No Stripe / RevenueCat integration.
78 | Onboarding Flow | Success screen (checkmark + next-steps checklist) | ✗ No |  | ✓ Done | ◑ In Progress | ◑ In Progress | ◑ In Progress | Done | Done | FULLY BUILT. Animated checkmark, confetti, next-steps checklist.
TRACKLYNK EXCLUSIVE
79 | Tracklynk Exclusive | Conversational AI assistant with quick-action pills | ✗ No |  | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie has NO AI assistant. This is Tracklynk's strongest differentiator. UI built, responses are mocked. Needs real LLM integration.
80 | Tracklynk Exclusive | Dark-first UI theme (premium feel vs Bouncie's flat white) | ✗ No |  | ✓ Done | ◑ In Progress | ◑ In Progress | ◑ In Progress | Done | Done | Consistent dark glassmorphism aesthetic. Bouncie is plain white/light. Clear visual differentiation.
81 | Tracklynk Exclusive | Framer Motion micro-interactions & spring animations | ✗ No |  | ✓ Done | ◑ In Progress | ◑ In Progress | ◑ In Progress | Done | Done | All screens use spring-based animations. Bouncie has flat, static transitions. UX quality advantage.

## Features - Screen - API mapping
Module | Feature ID | Feature Category | Feature or Sub Feature | Role | Web / Mobile | Version | Screen / Page | API/Websocket/Firebase | Status | Remarks/Comments
Authentication & Authorization |  |  | Login with Username & Password | ALL | Both | V1 | Login
|  |  | Login with Google (SSO integration) | ALL | Both | V1 | Login
|  |  | Login with Apple (SSO integration) | ALL | Both | V1 | Login
|  |  | Logout | ALL | Both | V1
|  |  | Forgot Password | ALL | Both | V1 | Forgot Password
|  |  | Verify Email, Send & Resend Verification Code | ALL | Both | V1 | Verify Email
|  |  | Security - token based authentication | ALL | Both | V1
Admin Module |  |  | Adminstrative Functionalities:
|  |  | Plans (CapEx, OpEx) & Device Prices management (VT, CT, PT) | TLAdmin | Web | V1 | Plans & Prices
|  |  | Features of the Devices management | TLAdmin | Web | V1 | Device Features
|  |  | Device Config management (MQTT Topics, Input, Output Payload) | TLAdmin | Web | V1 | Device Configs
|  |  | Vendor Management (Create, Update, Activate, Deactivate) | TLAdmin | Web | V1 | Vendors
|  |  | Order Management (Routing, Configs, TagId, Consumer Details) | TLAdmin | Web | V1 | Orders
|  |  | Order Notifications (Email, SMS, WhatsApp) to Vendor | TLAdmin | Both | V1 | Notifications
|  |  | Tag Activation validation | TLAdmin | Web | V1 | NA
Vendor Functionalities
Vendor Module |  |  | Update the Order with Delivery info with tracking info | Vendor |  | V1 | Orders
Consumer Functionalities
Registration & Onboarding |  |  | Consumer Registration | Consumer | Both | V1
|  |  | Purchase Tags + Payment Completion + Order Confirmation | Consumer |  | V1
|  |  | Receive Delivery & Tracking Info | Consumer |  | V1
|  |  | Receive Shipment + Acknowledgement (No Extra Step needed) | Consumer |  | V1
|  |  | Report or Return Damaged Tags (If found) (disable after certain period of time) | Consumer |  | V1
|  |  | Activation of Tags | Consumer |  | V1
|  |  | Entity Management (Vehicle, Asset, Child, Pet) | Consumer |  | V1
|  |  | Tag — Entity Mapping | Consumer |  | V1
Live Tracking & Map | TLL_FTR_1 | Map Display | Vehicle pin on live map | Consumer |  | V1 | Home / Map
| TLL_FTR_2 | Map Display | Live GPS refresh (15-second via 4G LTE-M) | Consumer |  | V1 | Home / Map
| TLL_FTR_3 | Map Display | Parked status chip + last engine-off timestamp | Consumer |  | V1 | Home / Map
| TLL_FTR_4 | Map Display | Current parked address (reverse-geocoded) | Consumer |  | V1 | Home / Map
| TLL_FTR_5 | Map Display | NWS severe weather badge on map | Consumer |  | V1 | Home / Map
| TLL_FTR_6 | Vehicle Card | Vehicle card (name, model, year) | Consumer |  | V1 | Home / Map
| TLL_FTR_7 | Vehicle Card | Fuel % health chip | Consumer |  | V1 | Home / Map
| TLL_FTR_8 | Vehicle Card | Battery health chip (Good/Bad) | Consumer |  | V1 | Home / Map
| TLL_FTR_9 | Vehicle Card | Engine status chip (check engine) | Consumer |  | V1 | Home / Map
| TLL_FTR_10 | Vehicle Card | Device connection chip (OBD online/offline) | Consumer |  | V1 | Home / Map
| TLL_FTR_11 | Vehicle Card | Vehicle card context menu (Notif / Details / Driving Stats) | Consumer |  | V1 | Home / Map
| TLL_FTR_12 | Map Controls | Map type toggle (Road / Satellite) | Consumer |  | V1 | Home / Map
| TLL_FTR_13 | Map Controls | Live Traffic overlay | Consumer |  | V1 | Home / Map
| TLL_FTR_14 | Map Controls | Speed Legend overlay | Consumer |  | V1 | Home / Map
| TLL_FTR_15 | Map Controls | Geo-Zone Areas overlay on map | Consumer |  | V1 | Home / Map
| TLL_FTR_16 | Map Controls | Vehicle pin tap → action sheet (Apple Maps / Google Maps / Uber / Lyft) | Consumer |  | V1 | Home / Map
| TLL_FTR_17 | Multi-Vehicle | Multiple vehicle switcher | Consumer |  | V1 | Home / Map
| TLL_FTR_82 | GPS Connectivity | ~10sec or real-time continuous GPS streaming — highest refresh rate in class | Consumer |  | V1 | Home / Map
| TLL_FTR_83 | GPS Connectivity | Engine-off low-power GPS pings every 30 minutes while parked | Consumer |  | V1 | Home / Map
| TLL_FTR_87 | GPS Connectivity | Live map auto-refresh included in base subscription — no upsell | Consumer |  | V1 | Home / Map
| TLL_FTR_88 | GPS Connectivity | Geographic coverage: United States, Canada, and Mexico (multi-carrier fallback) | Consumer |  | V1 | Home / Map
Trip History & Replay | TLL_FTR_19 | Trips List | Day View — all trips overlaid on single map for the day | Consumer |  | V1 | Trips List
| TLL_FTR_20 | Trips List | Daily aggregate stats (X trips · Y miles · VIEW DAY button) | Consumer |  | V1 | Trips List
| TLL_FTR_21 | Trips List | Individual trip rows (start time → end time, distance) | Consumer |  | V1 | Trips List
| TLL_FTR_22 | Trips List | Trip list date grouping | Consumer |  | V1 | Trips List
| TLL_FTR_23 | Trips List | Trip filter by date range | Consumer |  | V1 | Trips List
| TLL_FTR_24 | Trips List | Trip overflow menu (share, delete, flag) | Consumer |  | V1 | Trips List
| TLL_FTR_25 | Trip Detail | Route replay polyline on map | Consumer |  | V1 | Trip Details
| TLL_FTR_26 | Trip Detail | Color-coded speed bands (green/yellow/red vs posted limit) | Consumer |  | V1 | Trip Details
| TLL_FTR_27 | Trip Detail | Safety / driving score gauge (0–100, A/B/C/D) | Consumer |  | V1 | Trip Details
| TLL_FTR_28 | Trip Detail | Hard braking events with timestamp + count | Consumer |  | V1 | Trip Details
| TLL_FTR_29 | Trip Detail | Rapid acceleration events with timestamp + count | Consumer |  | V1 | Trip Details
| TLL_FTR_30 | Trip Detail | Speed alert events on route | Consumer |  | V1 | Trip Details
| TLL_FTR_31 | Trip Detail | Trip stats (distance, duration, idle time) | Consumer |  | V1 | Trip Details
| TLL_FTR_32 | Trip Detail | MPG / fuel economy per trip | Consumer |  | V1 | Trip Details
| TLL_FTR_33 | Trip Detail | Max speed for the trip | Consumer |  | V1 | Trip Details
| TLL_FTR_34 | Trip Detail | Start/end address labels on route | Consumer |  | V1 | Trip Details
| TLL_FTR_84 | Trip Logging | Unlimited trip retention with Day View + weekly/monthly summaries — exportable logs | Consumer |  | V1 | Trip Logging
| TLL_FTR_85 | Trip Logging | Continuous breadcrumb trail with color-coded speed bands + animated replay (play/pause/speed) | Consumer |  | V1 | Trip Logging
| TLL_FTR_125 | Trip Logging | One-tap or auto-tagged trip categorization (Business/Personal/Commute) with IRS-compliant mileage export | Consumer |  | V2 | Trip Logging
Vehicle Health & Diagnostics | TLL_FTR_35 | OBD Drill-Down | Fuel detail screen (large dial + notification threshold) | Consumer |  | V1 | OBD Health Drill-Down
| TLL_FTR_36 | OBD Drill-Down | Battery detail screen (voltage value + Normal/Low/Critical thresholds) | Consumer |  | V1 | OBD Health Drill-Down
| TLL_FTR_37 | OBD Drill-Down | Engine / DTC codes screen (code + plain-English description) | Consumer |  | V1 | OBD Health Drill-Down
| TLL_FTR_38 | OBD Drill-Down | Device status screen (IMEI, serial number, last comm timestamp + location) | Consumer |  | V1 | OBD Health Drill-Down
| TLL_FTR_89 | DTC & Engine | DTC code reading — decodes and categorizes by severity with suggested actions | Consumer |  | V1
| TLL_FTR_90 | DTC & Engine | Check engine light alerts — instant push with plain-language decoding and severity rating | Consumer |  | V1
| TLL_FTR_91 | Battery Health | Granular voltage-level monitoring with trend graph and user-defined threshold alerts | Consumer |  | V1
| TLL_FTR_92 | Fuel Monitoring | Fuel level reporting with automated fill-up detection and cost-per-mile calculation | Consumer |  | V1
| TLL_FTR_93 | Maintenance | Smart mileage/time reminders with custom maintenance task creation | Consumer |  | V1
| TLL_FTR_94 | Maintenance | VIN-based manufacturer recall alerts sourced from NHTSA database | Consumer |  | V1
| TLL_FTR_113 | Fuel Monitoring | Manual fuel cost entry with per-vehicle and fleet-wide fuel spend dashboards | Consumer |  | V1
| TLL_FTR_119 | Health Reporting | Quarterly health score (0–100) across 6 systems with trends and mechanic-validation insights | Consumer |  | V1
| TLL_FTR_120 | Predictive Maintenance | ML-driven failure forecasts from OBD trends — flags issues weeks before breakdown with cost estimate | Consumer |  | V1
| TLL_FTR_121 | Maintenance | Immutable timestamped maintenance log with QR code and Carfax/AutoCheck integration | Consumer |  | V1
Alerts & Notifications | TLL_FTR_39 | Notification Center | Drive tab (Hard Braking, Rapid Accel, Curfew, Trip Start/End, Speed) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_40 | Notification Center | Vehicle tab (Impact, Fuel Low, Battery, Geo-fence, DTC, Tamper, Distance, Idle) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_41 | Notification Center | Care tab (Distance, Idle Time, Trip Fuel Economy, Battery, DTC, Tamper) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_42 | Notification Delivery | Push notification delivery (FCM / APNs) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_43 | Alert Configuration | Hard Braking config (toggle + Excessive / Moderate / Light) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_44 | Alert Configuration | Rapid Acceleration config (toggle + 3-level sensitivity) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_45 | Alert Configuration | Speed alert config (Speed Limit + Speed Bands + Excessive MPH threshold) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_46 | Alert Configuration | Geo-Zone creation screen (circular zone, name, schedule) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_47 | Alert Configuration | Curfew creation screen (time window) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_48 | Alert Configuration | Trip Start / Trip End config (separate toggles) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_49 | Alert Configuration | Fuel Level alert slider (threshold %) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_50 | Alert Configuration | Battery alert config (Low & Critical / Critical Only toggle) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_51 | Alert Configuration | Distance Driven alert slider (mile threshold) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_52 | Alert Configuration | Idle Time alert config (Start/End + Total options) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_53 | Alert Configuration | NWS Weather alert toggle | Consumer |  | V1 | Alert Configuration
| TLL_FTR_54 | Alert Configuration | Impact Detection + emergency SMS contact | Consumer |  | V1 | Alert Configuration
| TLL_FTR_55 | Alert Configuration | DTC / Check Engine push toggle | Consumer |  | V1 | Alert Configuration
| TLL_FTR_56 | Alert Configuration | Tamper Detection toggle (OBD unplugged) | Consumer |  | V1 | Alert Configuration
| TLL_FTR_107 | Weather Alerts | NWS integration for severe weather with custom weather-trigger alerts filterable by severity level | Consumer |  | V1 | Alert Configuration
Driver Safety & Scoring | TLL_FTR_97 | Driving Behavior | True idle detection (RPM > 0, speed = 0) with customizable idle duration alerts | Consumer |  | V1
| TLL_FTR_98 | Driving Behavior | Speeding alerts mapped against posted limits + custom thresholds per geofence zone | Consumer |  | V1
| TLL_FTR_99 | Driving Behavior | 3-axis accelerometer with adjustable sensitivity for acceleration and braking | Consumer |  | V1
| TLL_FTR_100 | Driving Behavior | Lateral G-force monitoring (rough cornering) with adjustable sensitivity — logged per trip | Consumer |  | V1
| TLL_FTR_101 | Driving Behavior | Multi-schedule curfew windows with alerts on movement outside permitted hours | Consumer |  | V1
| TLL_FTR_102 | Safety Scoring | Composite safety score per trip + rolling 7-day/30-day driver profile by category | Consumer |  | V1
| TLL_FTR_103 | Safety Scoring | Family leaderboard with weekly rankings (privacy-first, within account only) | Consumer |  | V1
| TLL_FTR_115 | Coaching | 30-day rolling improvement score with trend analysis, weekly coaching, and milestone badges | Consumer |  | V2
| TLL_FTR_116 | Coaching | Camera-free distraction detection using GPS + accelerometer patterns — Low/Med/High risk score | Consumer |  | V2
| TLL_FTR_117 | Coaching | Lane change frequency profiling | Consumer |  | V2
| TLL_FTR_118 | Coaching | ML route familiarity classification (Familiar vs Unfamiliar) to weight safety scoring accurately | Consumer |  | V2
| TLL_FTR_122 | Driver Insights | ML driver archetypes (e.g., 'Highway Cruiser') across Aggressiveness, Consistency, Efficiency, Risk Tolerance | Consumer |  | V2
| TLL_FTR_123 | Driver Insights | Anonymous percentile ranking vs similar drivers with monthly progress updates | Consumer |  | V2
| TLL_FTR_129 | Eco Driving | Eco-score (0–100) on throttle, coasting, and shift habits with per-trip fuel savings and gamified badges | Consumer |  | V2
Safety & Security | TLL_FTR_104 | Accident Detection | Automatic high-G impact detection — triggers push, SMS to 5 emergency contacts, optional auto-call | Consumer |  | V1
| TLL_FTR_105 | Device Security | Instant multi-channel alert on OBD removal with last-known GPS coordinates | Consumer |  | V1
| TLL_FTR_106 | Roadside Assistance | Roadside assistance in base subscription — 3 claims/year (towing, jump-start, fuel delivery, lockout) | Consumer |  | V1
| TLL_FTR_108 | Anti-Theft | Engine-off GPS pings + geofence breach + towing detection — combined 'Theft Mode' multi-trigger | Consumer |  | V1
| TLL_FTR_128 | Accident Detection | Auto-generated crash report on impact: GPS, pre-crash speed, G-force, weather — one-tap PDF export | Consumer |  | V2
Fleet & Business Management | TLL_FTR_86 | Geofencing | Circular zones AND custom polygon geofences — draw any shape or quick-radius circle | Consumer |  | V1
| TLL_FTR_109 | Fleet Management | Unlimited vehicles on unified map with role-based access (Admin/Manager/Viewer) per vehicle group | Consumer |  | V1
| TLL_FTR_110 | Data Export | CSV and Excel export for trips, maintenance, fuel, and driver scores with tax/expense templates | Consumer |  | V1
| TLL_FTR_111 | Dispatch | Built-in dispatch pin-drop on map — assign vehicles to stops and track arrival/departure with ETA | Consumer |  | V1
| TLL_FTR_112 | Dispatch | Precise stop duration reporting with geo-tagged coordinates and configurable minimum stop threshold | Consumer |  | V1
| TLL_FTR_114 | Integrations | Open REST API with Webhooks and OAuth 2.0 — pre-built Google Sheets and Zapier integrations | Consumer |  | V1
| TLL_FTR_124 | Cost Tracking | Per-vehicle total cost tracking (fuel, maintenance, insurance, depreciation) with cost-per-mile alerts | Consumer |  | V2
| TLL_FTR_126 | Fleet Analytics | Per-vehicle utilization metrics (miles/month, days parked, sitting cost) with downsizing recommendations | Consumer |  | V2
| TLL_FTR_127 | Insurance & Compliance | 90-day telematics report with insurer-ready templates and predicted UBI discount estimate | Consumer |  | V2
| TLL_FTR_130 | Sustainability | Monthly CO2 calculation from fuel use with peer comparisons and offset recommendations; ESG reporting | Consumer |  | V2
Settings & Profile | TLL_FTR_57 | Account Management | My Profile screen (email, phone, password, Face ID) | Consumer |  | V1 | Settings / Profile
| TLL_FTR_58 | Account Management | Delete Account | Consumer |  | V1 | Settings / Profile
| TLL_FTR_59 | Vehicle Management | Vehicles management (add / edit / remove) | Consumer |  | V1 | Settings / Profile
| TLL_FTR_60 | Subscription | Subscription management | Consumer |  | V1 | Settings / Profile
| TLL_FTR_61 | Subscription | Payment details (billing history, payment method) | Consumer |  | V1 | Settings / Profile
| TLL_FTR_62 | App Preferences | Units setting (Imperial / Metric, MPG / L/100km / km/L) | Consumer |  | V1 | Settings / Profile
| TLL_FTR_63 | App Preferences | App Appearance (Light / Dark / System with visual previews) | Consumer |  | V1 | Settings / Profile
| TLL_FTR_64 | Support | Support / live chat | Consumer |  | V1 | Settings / Profile
| TLL_FTR_65 | Support | Feedback submission | Consumer |  | V1 | Settings / Profile
| TLL_FTR_66 | Legal | Privacy Policy / Terms of Service | Consumer |  | V1 | Settings / Profile
| TLL_FTR_67 | App Info | App version display | Consumer |  | V1 | Settings / Profile
| TLL_FTR_68 | Security | Two-Factor Authentication setup flow | Consumer |  | V1 | Settings / Profile
| TLL_FTR_69 | Security | Active Sessions management (view + revoke devices) | Consumer |  | V1 | Settings / Profile
| TLL_FTR_70 | Privacy | Privacy & Data controls | Consumer |  | V1 | Settings / Profile
| TLL_FTR_71 | App Info | What's New / Changelog screen | Consumer |  | V1 | Settings / Profile
| TLL_FTR_95 | App Preferences | Emission testing predictions — not supported (low demand; keeps UX simple) | Consumer |  | V1 | Settings / Profile

## Schedule
| Brainstorming |  | Requirements Analysis |  | Design |  | Development |  | QA |  | Deployment |  | Demo & Feedback |  | Status
| Start Date | End Date | Start Date | End Date | Start Date | End Date | Start Date | End Date | Start Date | End Date | Start Date | End Date | Start Date | End Date
Authentication & Authorization | Completed | Completed | Completed | Completed | Completed | Completed | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 | Devlopment InProgress
Registration & Onboarding Flow | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06
Live Tracking & Map | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08
Trip History & Replay | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-06 | 2026-05-07 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13
Vehicle Health & Diagnostics | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-15
Alerts & Notifications | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-13 | 2026-05-14 | 2026-05-18 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-20
Driver Safety & Scoring | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-15 | 2026-05-18 | 2026-05-21 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22
Safety & Security | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-14 | 2026-05-19 | 2026-05-20 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-27
Fleet & Business Management | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-21 | 2026-05-22 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-05-29
Settings & Profile | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-25 | 2026-05-26 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01
| Start Date | End Date
Simulator for Customer Demos | 2026-05-20: 2026-05-18; 2026-05-20: 2026-05-27

## Flow Registry
Flow ID | Module | Canonical Flow Name | Variants Covered | Description | Build Status | Prototype Coverage | Screen / Route in Build | Priority | Spec Completeness (rolled up) | Prototype Evidence | Original Gaps / Missing | Source / Spec Link | Issue / Ticket | Owner | Last Verified | Notes
F-001 | 1 – Authentication & Authorization | OAuth Sign In / Sign Up | Provider: Apple ¦ Google ; Mode: Sign in ¦ Sign up | User authenticates via Apple or Google OAuth, either as a new account (sign-up) or returning user (sign-in). | Shipped to Prototype | Yes | Sign-in screen → 'Continue with Apple' ; Sign-in screen → 'Continue with Google' ; Sign-up screen → 'Continue with Apple' ; Sign-up screen → 'Continue with Google' | P0 | Partially Specified | #6: Apple OAuth button visible on Create-account screen ¦ #8: Google OAuth button visible ¦ #21: Same component as sign-in; OAuth path ¦ #22: Same component as sign-in; OAuth path | #6: Apple auth failure and account-already-linked error states not described. Loading/spinner state not specified. ¦ #8: Google auth failure, account mismatch, and revoked-permission error states not documented. ¦ #21: Account-linking for a user who already has an email account not described. Name population from Apple not confirmed. ¦ #22: Account-linking with existing email and permission scope not described. |  |  |  | 2026-05-04
F-002 | 1 – Authentication & Authorization | Sign In with Email & Password | — | User signs in to an existing account using email + password/ forgot password | Shipped to Prototype | Yes | Sign-in screen → email + password | P0 | Not Specified | #7: Email + password fields shown; 'Sign in' link present | #7: No dedicated returning-user sign-in screen is described in any document. Forgot-password flow entirely absent. |  |  |  | 2026-05-04
F-003 | 1 – Authentication & Authorization | Sign In with Face ID / Biometric | — | Returning user re-enters the app via Face ID / fingerprint. | Shipped to Prototype | Yes | Sign-in screen → 'Sign in with Face ID' card | P0 | Partially Specified | #5: 'Sign in with Face ID' + 'Use Face ID — Quick, secure re-entry' | #5: First-time biometric enrollment flow not described. Fallback path when biometric fails (e.g., fall back to password) not specified. |  |  |  | 2026-05-04
F-004 | 1 – Authentication & Authorization | Set Up & Toggle Two-Factor Authentication | Action: Enable ¦ Disable ¦ View manual key ¦ Save backup codes | User enables or disables 2FA via authenticator app or SMS, including manual-key copy and backup-code storage. | Shipped to Prototype | Partial | Settings → 2FA → 'View Backup Codes' / 'Save Your Backup Codes' ; Settings → ACCOUNT & SECURITY → Two-Factor Auth toggle ; Settings → Two-Factor Auth → Manual Key ; Settings → Two-Factor Auth → setup wizard | P1 | Partially Specified | #1: 'Manual Key' / 'Authenticator app' UI present in 2FA setup ¦ #2: 'Two-Factor Auth · Off' toggle in Settings ¦ #4: Authenticator app + SMS + Backup Codes screens all in bundle ('Choose Method', 'Verify', 'Backup Codes') ¦ #12: 'View Backup Codes' + 'Save Your Backup Codes' screens in bundle | #1: No flow described for how the manual key is displayed, copied, or validated in an authenticator app. ¦ #2: Re-authentication / confirmation step before disabling not described. ¦ #4: 2FA method (authenticator app, SMS, or email?) not specified. QR-code pairing flow not described. Re-authentication before enabling not confirmed. ¦ #12: Copy-to-clipboard, regenerate, and print backup-codes flows not described. |  |  |  | 2026-05-04
F-005 | 1 – Authentication & Authorization | Enable Biometric Login (Settings) | Method: Face ID ¦ Fingerprint | User opts into biometric re-entry from Security settings. | Shipped to Prototype | Yes | Settings → ACCOUNT & SECURITY → Face ID / Biometrics | P0 | Partially Specified | #3: 'Face ID / Biometrics' row + 'Use Face ID' CTA on returning-user card | #3: Platform differences (iOS Face ID vs. Android fingerprint) and OS-level permission prompts not documented. |  |  |  | 2026-05-04
F-006 | 1 – Authentication & Authorization | Manage Active Sessions | Action: View ¦ Sign out other sessions | User reviews logged-in devices and signs out other sessions. | Shipped to Prototype | Yes | Settings → Active Sessions ('3 devices') ; Settings → Active Sessions → 'Sign out other sessions' | P1 | Partially Specified | #9: 'All other sessions removed' confirmation string in bundle ¦ #11: Active Sessions row shown in Settings; 'Other Sessions' / 'This Device' / 'Last seen' strings in bundle | #9: Confirmation dialog and success/failure feedback not described. ¦ #11: Session detail data (device type, IP, last-active timestamp, location) not specified. |  |  |  | 2026-05-04
F-007 | 1 – Authentication & Authorization | Sign Out of App | — | User signs out of the current device. | Backlog | No | — | P0 | Not Specified | #10: No 'Sign out' action visible in Settings; account row shows email but no logout CTA. Likely missing. | #10: Sign-out button location, confirmation step, and post-sign-out destination not described in any document. |  |  |  | 2026-05-04
F-008 | 2 – Registration & Onboarding | View Welcome Onboarding Carousel | Slides: Welcome ¦ Everything you need ¦ Simple pricing | First-time user steps through the 3-slide intro carousel. | Shipped to Prototype | Yes | Home → 3-slide carousel | P0 | Fully Specified | #26: Slides: TrackLynk welcome / Everything you need / Simple pricing |  |  |  |  | 2026-05-04
F-009 | 2 – Registration & Onboarding | Toggle Monthly / Annual Billing | Period: Monthly ¦ Annual | User switches the billing period on the pricing slide / plan picker. | Shipped to Prototype | Yes | Pricing carousel slide / Plan picker | P0 | Fully Specified | #24: Monthly / Annual toggle on slide 3 + in plan picker; 'SAVE $21' label |  |  |  |  | 2026-05-04
F-010 | 2 – Registration & Onboarding | Select Pricing Plan | Tier: Personal ¦ Business ¦ Fleet | User picks a subscription tier during onboarding. | Shipped to Prototype | Yes | Onboarding → Choose Your Plan (Personal / Business / Fleet) | P0 | Partially Specified | #20: Three tier ids in bundle: id:'personal', id:'business', id:'fleet' | #20: Enterprise (custom) plan selection flow not described. Payment entry and confirmation not shown. Free-trial or promotional code redemption not described. |  |  |  | 2026-05-04
F-011 | 2 – Registration & Onboarding | Create Account with Email | — | User completes the email-signup form (first/last name, mobile, email, password). | Shipped to Prototype | Yes | Sign-up screen → email form (5 fields) | P0 | Partially Specified | #16: First name / Last name / Mobile / Email / Password fields visible | #16: Password strength validation rules not specified. Mobile number format/validation not described. Terms acceptance confirmation step not shown. |  |  |  | 2026-05-04
payment page + confirmation + tracking
F-012 | 2 – Registration & Onboarding | Add Vehicle by VIN ( adding entites ) | Input method: Scan barcode ¦ Manual entry | User adds a vehicle either by scanning the VIN barcode with the camera or typing it manually. | Shipped to Prototype | Yes | Onboarding → Add Your Vehicle → Enter VIN ; Onboarding → Add Your Vehicle → Scan VIN barcode | P0 | Partially Specified | #13: 'Enter your VIN' input string in bundle ¦ #14: 'Scan VIN barcode' string in bundle | #13: Invalid VIN format error state, VIN lookup failure, and unsupported vehicle message not described. ¦ #14: Camera permission denial flow, failed scan / retry, and poor lighting fallback not described. |  |  |  | 2026-05-04
F-013 | 2 – Registration & Onboarding | Name Vehicle (Nickname) | — | User assigns a friendly nickname during onboarding. | Shipped to Prototype | Yes | Onboarding → Name your vehicle | P0 | Fully Specified | #18: 'Name your vehicle' + 'Nickname' input in bundle |  |  |  |  | 2026-05-04
F-014 | 2 – Registration & Onboarding | Pair OBD Device + Setup Wizard | Steps: Find OBD port → Plug in → Bluetooth pair → Start engine | User completes the 4-step device-setup wizard, ending in successful Bluetooth pairing. | Shipped to Prototype | Yes | Onboarding → Connect Device → 4-step wizard ; Onboarding → Connect Device → Bluetooth | P0 | Partially Specified | #15: 'Find the OBD port' → 'Plug in your device' → 'Pairing…' → 'Start your engine' (4 steps) ¦ #19: 'Bluetooth pairing' + 'Simulate Pairing' + 'Pairing…' states | #19: Pairing failure states, device-not-found flow, and Bluetooth permission-denied handling not described. |  |  |  | 2026-05-04
F-015 | 2 – Registration & Onboarding | Skip Device Pairing | — | User defers OBD pairing and proceeds to the app shell. | Shipped to Prototype | Yes | Onboarding → Connect Device → 'Skip for now' | P1 | Partially Specified | #23: 'Skip for now' string in device-setup screens | #23: How user is reminded to complete setup later (nudge notification, banner, incomplete indicator) not described. |  |  |  | 2026-05-04
F-016 | 2 – Registration & Onboarding | View Onboarding Completion | — | User sees the 'One last thing' / Open TrackLynk completion screen. | Shipped to Prototype | Yes | Onboarding → 'One last thing' completion | P0 | Fully Specified | #25: 'One last thing' + 'Open TrackLynk' string in bundle |  |  |  |  | 2026-05-04
F-017 | 2 – Registration & Onboarding | Enter Demo / Test Drive Mode | — | User skips signup and explores the app with sample data. | Shipped to Prototype | Yes | Home → 'Test drive the app' | P0 | Not Specified | #17: Demo mode button on home; takes user straight into app shell | #17: Demo mode content, limitations, data shown, and how to exit or convert to a real account not described in any document. |  |  |  | 2026-05-04
F-018 | 3 – Live Tracking & Map | View Live Vehicle on Home Map | Sub-views: Auto-locate ¦ Live position ¦ Current address | User opens Home and sees the vehicle's real-time GPS position, address, and trip status. | Shipped to Prototype | Partial | Home → Live Trip card ; Home → Map + Live Trip card ; Home → Map view (centered on vehicle) | P0 | Partially Specified | #27: Google Maps embed present but fails to load on Vercel host (key not allow-listed). UI scaffolding exists. ¦ #31: 'Candace Ln · 5 mins away' shown on Live Trip card ¦ #33: 'Live Trip' + 'Morning Commute' + 'GO' button on Home | #27: Target zoom level, animation behavior, and what happens when vehicle location is stale not described. ¦ #31: Address display format, update cadence, and behavior when address lookup fails (no reverse geocode result) not specified. |  |  |  | 2026-05-04
F-019 | 3 – Live Tracking & Map | Toggle Real-Time Traffic Overlay | — | User enables a live traffic layer over the map. | Designed Not Built | Partial | Home → Map | P1 | Fully Specified | #34: Google Maps embed supports traffic layer but layer toggle not visible in UI; cannot verify with broken map. |  |  |  |  | 2026-05-04
F-020 | 3 – Live Tracking & Map | Switch Active Vehicle on Map | — | User picks a different vehicle from a multi-vehicle account to focus the map on. | Backlog | No | — | P1 | Partially Specified | #28: Multi-vehicle dashboard listed as a tier feature ('Multi-vehicle dashboard') but no in-app vehicle switcher on the map. | #28: Whether the map re-centers, the data drawer updates, and transition animation behavior when switching vehicles not fully described. |  |  |  | 2026-05-04
F-021 | 3 – Live Tracking & Map | View Engine-Off Location Pings | — | User sees parked-vehicle location updated periodically while engine is off. | Backlog | No | — | P1 | Partially Specified | #32: No engine-off ping interval visible. Bundle has 'Engine running — device is powering up' but not engine-off pings. | #32: How the UI distinguishes a live-tracking state vs. an engine-off ping state (e.g., greyed-out marker, timestamp of last ping) not described. |  |  |  | 2026-05-04
F-022 | 3 – Live Tracking & Map | View All Trips on Day-View Canvas | — | User opens a day-view of all trips on a single canvas. | Backlog | No | — | P2 | Partially Specified | #30: No day-view canvas/timeline of trips. Trips tab uses a flat list grouped by Today / Yesterday / date. | #30: Navigation path to Day View from Home or Trips not explicitly described. Interaction within Day View (tap a trip, expand summary) not documented. |  |  |  | 2026-05-04
F-023 | 3 – Live Tracking & Map | Use Conversational / Voice Interface | Surface: Quick-action chips ¦ Voice command | User asks the app for vehicle status using a chat or voice surface (chips on Home, voice query, etc.). | Shipped to Prototype | Partial | Home → quick-action chip row | P2 | Not Specified | #29: Chips: 'Check fuel', 'Trips today', 'Speed alerts', 'Find parking', 'Diagnostics', 'Device health'. Conversational suggestions, but no voice input. | #29: Supported query types, NLP capabilities, response format, fallback for unrecognised queries, and internet-dependency behavior not described. |  |  |  | 2026-05-04
F-024 | 4 – Trip History & Replay | View Trip History List | — | User sees a chronological list of trips grouped by Today / Yesterday / past dates. | Shipped to Prototype | Yes | Trips tab → list | P0 | Fully Specified | #42: Trip list with grouping (TODAY / YESTERDAY / dates), per-trip distance, duration, A/B/C grade |  |  |  |  | 2026-05-04
F-025 | 4 – Trip History & Replay | Filter Trip History by Date Range | — | User filters the trip list to a custom date range. | Shipped to Prototype | Yes | Trips → Filter button / DATE RANGE picker | P1 | Partially Specified | #35: Filter icon top-right on Trips header; 'Filter Trips' + 'DATE RANGE' strings | #35: Filter options beyond date range (by vehicle, score grade, event type) not specified. Empty-state when no trips match filter not described. |  |  |  | 2026-05-04
F-026 | 4 – Trip History & Replay | View Trip Detail | Components: Route map ¦ Animated replay ¦ Color-coded speed bands ¦ Per-trip score ¦ Safety events ¦ Per-trip fuel cost | User taps a trip to see route map, animated replay, speed-banded route polyline, score, safety events, and trip cost. | Shipped to Prototype | Partial | Trip Detail screen ; Trip Detail → Route ; Trip Detail → Route map ; Trip Detail → Score + EVENTS section | P0 | Partially Specified | #36: ROUTE START/END addresses shown; map fails to load so animated replay can't be verified. Bundle: 'Route replay (90 days)' ¦ #37: Speed events listed in trip but no color-coded speed band on the route polyline visible in UI. ¦ #39: Driving Score (A) + EVENTS section ('Clean drive · No events recorded' for this sample) ¦ #40: Trip Detail shows distance/duration/avg-speed/max-speed/score — no fuel cost. ¦ #41: Trip detail with title/date/range, distance, duration, avg/max speed, score, route start/end, events | #36: Playback controls (play, pause, scrub, playback speed) not described. Whether replay is a separate mode or inline not specified. ¦ #37: Speed band color legend, speed threshold definitions for each band, and interactive tap-on-segment behavior not specified. ¦ #40: Fuel price source (manual input, geo-based pump prices, user preference?), vehicle fuel type handling, and fuel cost methodology not described. |  |  |  | 2026-05-04
F-027 | 4 – Trip History & Replay | View Trip Summary by Period | Period: Weekly ¦ Monthly | User sees aggregate trip stats (count / distance / drive time) for a period. | Shipped to Prototype | Partial | Trips tab → top stats card | P2 | Not Specified | #38: No monthly summary screen. Aggregate stats card on Trips tab shows raw counts only (Trips / Distance / Drive Time). ¦ #43: Aggregate card: 6 Trips / 22.7 mi / 2h 38m. Implicitly weekly but not labelled as such. | #38: Access path, displayed metrics, date range selection, and visual format for monthly summary not described in any document. ¦ #43: Access path, displayed metrics, and visual format for weekly summary not described in any document. |  |  |  | 2026-05-04
F-028 | 5 – Vehicle Health & Diagnostics | View Vehicle Health Score | Sub-views: Score ¦ Factor breakdown | User sees the 0–100 vehicle health score and its weighted factor breakdown (6 factors). | Shipped to Prototype | Yes | Health → Vehicle → 6 factors ; Health → Vehicle → score 84/100 | P0 | Fully Specified | #57: Vehicle score ring 84/100 + B+ grade + 'Top 28% of vehicles' + '+2 pts vs last month' ¦ #58: Six diagnostics factors with weights (Fault Codes 30%, Battery 20%, Engine Temp 15%, Fuel System 15%, Maintenance 10%, Mileage 10%) |  |  |  |  | 2026-05-04
F-029 | 5 – Vehicle Health & Diagnostics | View Diagnostic Factor Detail | Factor: Battery Health ¦ Engine Temperature ¦ Fuel System Health ¦ Active Fault Codes ¦ Maintenance Compliance ¦ Overall Mileage | User drills into any single diagnostic factor for current value, trend, and improvement tip. | Shipped to Prototype | Partial | Health → Vehicle → Battery Health ; Health → Vehicle → Engine Temperature ; Health → Vehicle → Fuel System Health | P1 | Partially Specified | #49: Current voltage + 'Good' qualitative label shown. No trend graph. ¦ #51: 'Engine Temperature · Running in normal range · 82' ¦ #54: 'Fuel System Health · O2 sensor reading lean · 74' | #49: Time window for the trend graph (7 days? 30 days?), interactive zoom/scrub, and what constitutes a 'healthy' voltage range not specified. ¦ #51: Temperature units (°F/°C), thresholds for each risk tier, and what overheating looks like in the UI not described. ¦ #54: How fuel trim and O2 sensor readings are translated into a consumer-friendly score or status message not described in any document. |  |  |  | 2026-05-04
F-030 | 5 – Vehicle Health & Diagnostics | View DTC Fault Codes | State: Active ¦ Cleared / History | User sees current DTC fault codes with severity and the cleared-codes history. | Shipped to Prototype | Yes | Health → Vehicle → 'View code history' link ; Health → Vehicle → Active Fault Codes | P1 | Partially Specified | #48: 'Active Fault Codes · No active codes · 1 recently cleared' + 'Catalyst Efficiency Below Threshold' as sample DTC ¦ #50: 'View code history' link under Active Fault Codes card | #50: How cleared codes are visually differentiated from active codes, and whether users can manually clear a code from the app, not described. |  |  |  | 2026-05-04
F-031 | 5 – Vehicle Health & Diagnostics | Manage Maintenance Tasks | Action: View timeline ¦ Add custom task ¦ Mark complete | User views the maintenance schedule, adds custom reminders, and marks tasks done. | Shipped to Prototype | Partial | Health → Vehicle → Maintenance Schedule | P1 | Partially Specified | #44: Maintenance Schedule shown but no 'Add custom task' affordance. ¦ #45: Maintenance items show 'Due soon' / 'Due in ~200 mi' but no 'Mark as completed' control. ¦ #55: 'Maintenance Schedule · Next 4 items' (Oil Change, Tire Rotation, Air Filter, Brake Fluid) | #44: Editing, completing, and deleting a custom task not described. Whether tasks sync across multiple vehicles not specified. ¦ #45: No flow described for marking completion, resetting schedule, or logging service history. Mileage reset logic not described. |  |  |  | 2026-05-04
F-032 | 5 – Vehicle Health & Diagnostics | View Fuel Stats | Scope: Per-trip MPG ¦ Current fuel level ¦ Weekly efficiency trend | User sees fuel-related metrics across trips and time periods. | Designed Not Built | Partial | Home → quick-action 'Check fuel' chip | P2 | Partially Specified | #52: Trip detail does not include MPG. No fuel-economy strings beyond 'Fuel tracking & expense log' as a tier feature. ¦ #53: Chip exists but no fuel-level gauge screen confirmed. ¦ #59: No fuel efficiency trend chart. Only mileage card. | #52: How MPG is calculated (OBD fuel flow data vs. GPS distance + fill-up detection) and handling of vehicles without fuel flow PIDs not specified. ¦ #53: How vehicle compatibility is communicated, what is shown for incompatible vehicles, and fill-up event confirmation flow not described. ¦ #59: Where the weekly trend is displayed (Health tab? Trips tab?), chart type, and time period selection not described. |  |  |  | 2026-05-04
F-033 | 5 – Vehicle Health & Diagnostics | View NHTSA Recall Alerts | — | User sees recall alerts sourced from the NHTSA database for their VIN. | Backlog | No | — | P1 | Fully Specified | #56: No NHTSA recall integration in build. Listed as registry feature but absent from prototype. |  |  |  |  | 2026-05-04
F-034 | 5 – Vehicle Health & Diagnostics | Navigate to Service from Recall | — | User taps a recall alert and is routed to a service-scheduling surface. | Backlog | No | — | P1 | Partially Specified | #46: No NHTSA recall flow in build (no 'recall' / 'NHTSA' strings in bundle). | #46: Whether the link opens in an in-app WebView or external browser not described. Native scheduling integration (not just a link) not specified. |  |  |  | 2026-05-04
F-035 | 5 – Vehicle Health & Diagnostics | Set Battery Voltage Alert Threshold | — | User configures the voltage at which a low-battery alert fires. | Backlog | No | — | P2 | Partially Specified | #47: Battery Health card shows current voltage and a 20%-weight contribution to score, but no threshold setting. | #47: Where this setting is located (Health screen vs. Alerts settings vs. both) not specified. Default threshold value not documented. |  |  |  | 2026-05-04
F-036 | 6 – Alerts & Notifications | Configure Notification Channels | Channel: Push ¦ Email ¦ SMS ; Frequency: Realtime ¦ Daily digest ¦ Weekly digest | User toggles which channels receive alerts and the digest frequency. | Shipped to Prototype | Partial | Settings → NOTIFICATIONS section (whole) | P0 | Partially Specified | #62: No per-channel email toggle. Bundle has 'Email support' but not 'Email alerts' channel. ¦ #63: Notifications block exists but no master push-on/off switch confirmed in this prototype. ¦ #64: 'SMS text message' string is part of 2FA flow only, not an alerts channel. ¦ #75: No daily/weekly digest frequency setting. | #62: Which alert types support email delivery and minimum/maximum email frequency not documented. ¦ #63: Granularity of per-type toggles and OS-level permission handling (iOS critical alerts, Android notification channels) not described. ¦ #64: Which specific alert types support SMS delivery and carrier costs or opt-out handling not listed. ¦ #75: Which alert types are eligible for digest mode and how conflicting digest/immediate settings are resolved not specified. |  |  |  | 2026-05-04
F-037 | 6 – Alerts & Notifications | Configure Alert Rules | Rule: Speed threshold ¦ Geofence mode ¦ Low-fuel threshold ¦ Quiet hours ¦ Severe-weather severity filter | User customises per-rule thresholds, modes, and time windows for alerts. | Shipped to Prototype | Partial | Settings → NOTIFICATIONS → Geofence Alerts ; Settings → NOTIFICATIONS → Speed Alerts | P1 | Partially Specified | #60: Toggle present; mode (push/SMS/silent log) not exposed in this prototype. ¦ #61: Toggle present; threshold input not visible in prototype. ¦ #76: No low-fuel threshold setting. ¦ #77: No quiet hours setting. ¦ #78: No severe-weather severity filter (no severe weather feature). | #60: Where per-zone alert settings are accessed (geofence edit screen vs. Alerts settings) and what 'silent log' means for downstream reporting not fully described. ¦ #61: Whether threshold is configured in Alerts settings, Geofence settings, or both not clear. Per-geofence vs. global precedence not specified. ¦ #76: Where this setting is located (Alerts settings vs. Vehicle Health section) and default threshold value not specified. ¦ #77: Support for multiple quiet windows, weekday vs. weekend schedules, and timezone handling not described. ¦ #78: Severity levels and their definitions, default setting, and how NWS severity tiers map to the filter options not described in any document. |  |  |  | 2026-05-04
F-038 | 7 – Driver Safety & Scoring | View Driver Score | Sub-views: Score ¦ Factor breakdown ¦ Trend over time | User sees the 0–100 driver score, weighted factor breakdown (7 factors), and trend with month-over-month delta. | Shipped to Prototype | Yes | Health → Driver → 7 factors with weights ; Health → Driver → score 78/100 ; Health → Driver → trend + monthly delta | P0 | Partially Specified | #83: Driver score 78/100 + B 'Good' + 'Top 32% of drivers' ¦ #84: Speeding 25% / Hard Braking 20% / Rapid Accel 15% / Harsh Cornering 15% / Time of Day 10% / Miles Driven 10% / Idle Time 5% ¦ #85: '+4 pts vs last month' + 7-day mini chart | #85: Time period covered by the trend line, chart type, and whether the user can drill into specific time ranges not described. |  |  |  | 2026-05-04
F-039 | 7 – Driver Safety & Scoring | View Driver Profile (Rolling Window) | Period: 7-day ¦ 30-day | User picks a rolling time window to evaluate their driving profile against. | Shipped to Prototype | Partial | Health → Driver score (rolling) ; Health → Driver → 7-DAY trend | P1 | Partially Specified | #81: '30-day trip history' string present (tier feature); 30-day rolling profile UI not explicit. ¦ #82: '7-DAY · +6 pts' mini chart on driver score card | #81: Where the 30-day profile is displayed on screen, how it is visually differentiated from the real-time score, and drill-down detail not described. ¦ #82: Same gap as 30-day profile — display location, chart type, and interaction not described. |  |  |  | 2026-05-04
F-040 | 7 – Driver Safety & Scoring | View Per-Trip Driver Score Grade | Grade: A ¦ B ¦ C ¦ D | User sees a letter-grade chip per trip in the trip list. | Shipped to Prototype | Yes | Trips list → letter grade chip | P0 | Fully Specified | #91: Per-trip A / B / C grade visible on each row in Trips list |  |  |  |  | 2026-05-04
F-041 | 7 – Driver Safety & Scoring | View Per-Trip Safety Events | Event type: Hard Braking ¦ Harsh Cornering ¦ Rapid Acceleration ¦ Speeding | User sees the safety events recorded on a single trip, with severity and contributing impact on score. | Shipped to Prototype | Partial | Health → Hard Braking factor + Trip Detail EVENTS ; Health → Harsh Cornering factor ; Health → Rapid Accel factor ; Health → Speeding Events factor | P1 | Partially Specified | #87: Hard Braking shown as factor with event count; trip-detail EVENTS section appears empty for sample trip ('Clean drive') ¦ #88: Same pattern: factor card present, trip-detail per-event view not verified for cornering specifically ¦ #92: Factor card present; trip-detail per-event view not verified ¦ #93: 'Speeding Events · 2 events this week · 1 event at 82 mph — high severity' | #87: Whether events are shown on the trip map as pins (vs. list only), severity differentiation (e.g., 0.3g vs. 0.6g), and event-level tips not described. ¦ #88: No explicit UI for cornering events in TripDetail described in any document; feature is confirmed in Feature Set PDF but display not specified. ¦ #92: Event severity differentiation and whether events are visualised on the trip map not described. Consistent gap with hard braking events. ¦ #93: Whether event location is shown on the trip map as a pin or listed only as metadata not specified. Event count vs. duration not differentiated. |  |  |  | 2026-05-04
F-042 | 7 – Driver Safety & Scoring | View Idle Time Per Trip | — | User sees idle time as a sub-factor on the Driver score. | Shipped to Prototype | Yes | Health → Idle Time factor | P1 | Partially Specified | #89: 'Idle Time · 4 min avg idle per trip · 88 (5% wt.)' | #89: Whether 'average idle time' shown as a stat pill refers to OBD true idle (RPM>0, speed=0) vs. engine-off time not clarified. |  |  |  | 2026-05-04
F-043 | 7 – Driver Safety & Scoring | View Per-Factor Improvement Tip | — | User reads an actionable tip per scoring factor with quantified +N pts potential. | Shipped to Prototype | Yes | Health → factor row → '+N pts potential' tip | P1 | Partially Specified | #90: 'More following distance reduces hard-braking events. +6 pts potential' (sample) | #90: Whether tips are contextual/dynamic per user data or static per factor not described. Tip content for all 7 factors not fully documented. |  |  |  | 2026-05-04
F-044 | 7 – Driver Safety & Scoring | View Family Leaderboard | Period: Weekly | User sees household drivers ranked by score. | Backlog | No | — | P2 | Partially Specified | #86: No leaderboard / family rankings. Only single-user score. | #86: How to access the leaderboard, how family members are added/invited, and whether the leaderboard is opt-in not described. |  |  |  | 2026-05-04
F-045 | 7 – Driver Safety & Scoring | Adjust Detection Sensitivity | Event type: Hard Braking ¦ Rapid Acceleration | User tunes the threshold at which a brake or accel event is logged. | Backlog | No | — | P3 | Not Specified | #79: No detection-sensitivity slider. Hard-braking shown as a passive factor only. ¦ #80: No detection-sensitivity slider for rapid acceleration. | #79: No UI or navigation path for adjusting braking sensitivity described in any document, despite being listed as a feature. ¦ #80: Same gap as hard braking sensitivity — no UI or flow described in any document. |  |  |  | 2026-05-04
F-046 | 8 – Safety & Security | Manage Geofence Zones | Action: Create circular ¦ Create polygon ¦ Edit ¦ Delete | User creates and manages geofence zones around home, work, school, etc. | Backlog | No | — | P1 | Partially Specified | #96: Geofence Alerts toggle exists but no zone creation UI. ¦ #97: 'polygon' only appears as Google Maps event type, not as a polygon-zone creator. ¦ #98: No geofence list / edit / delete UI. | #96: Step-by-step creation flow (where accessed, how radius is set, naming screen, save confirmation) not described in detail. ¦ #97: Drawing UX (tap to add vertex, drag to adjust, close polygon, undo) not described. Maximum vertex count not specified. ¦ #98: No edit or delete flow described for geofences in any document. Whether edit re-uses the creation UI or has a separate screen not specified. |  |  |  | 2026-05-04
F-047 | 8 – Safety & Security | Configure Curfew / Operating Hours | — | User defines a curfew window during which vehicle use triggers an alert. | Designed Not Built | Partial | Health → Time of Day factor | P2 | Partially Specified | #94: 'No late-night driving' shown as a factor outcome, not as a configurable curfew window. | #94: Number of simultaneous windows supported, timezone handling, and fleet vs. personal account behaviour not specified. Overlaps with Module 9 fleet use case. |  |  |  | 2026-05-04
F-048 | 8 – Safety & Security | Configure Emergency Contacts | Limit: Up to 5 | User registers emergency contacts to be notified on crash / SOS events. | Backlog | No | — | P1 | Partially Specified | #95: No emergency contacts UI in prototype. | #95: Where in the app emergency contacts are configured (Settings? Safety section?) not described. Contact verification or consent flow not specified. |  |  |  | 2026-05-04
F-049 | 8 – Safety & Security | Trigger SOS Emergency Call | — | User triggers an in-app SOS emergency call. | Backlog | No | — | P1 | Partially Specified | #107: No SOS button found. | #107: Where the SOS button is located in the UI not described. Confirmation step before dialling 911 not specified. |  |  |  | 2026-05-04
F-050 | 8 – Safety & Security | Request Roadside Assistance | Service: Tow ¦ Jump start ¦ Fuel delivery | User requests a roadside-assistance service from inside the app. | Backlog | No | — | P2 | Partially Specified | #104: No roadside assistance flows. ¦ #105: No roadside assistance flows. ¦ #106: No roadside assistance flows. | #104: Where in the app roadside assistance is accessed, fuel type options, and ETA or claim-status tracking not described. ¦ #105: UI entry point, provider network, ETA display, and claim confirmation not described. ¦ #106: Where roadside assistance is accessed in the UI, vehicle location confirmation, provider dispatching, claim-status tracking not described. |  |  |  | 2026-05-04
F-051 | 8 – Safety & Security | View Roadside Claims Remaining | — | User sees how many included roadside-assistance claims they have left this period. | Backlog | No | — | P3 | Not Specified | #108: No claims-remaining counter. | #108: No UI or flow described for viewing claim balance, claim history, or claim renewal date. |  |  |  | 2026-05-04
F-052 | 9 – Fleet & Business Management | Switch Active Vehicle in Fleet | — | Fleet user picks the active vehicle to focus the map and dashboards on. | Backlog | No | — | P2 | Fully Specified | #115: No fleet vehicle switcher on map. |  |  |  |  | 2026-05-04
F-053 | 9 – Fleet & Business Management | View Fleet Dashboard (Web Portal) | — | Fleet admin opens the web portal dashboard. | Out of Scope | No | — | P3 | Partially Specified | #116: No web portal in this prototype (mobile only). | #116: Specific dashboard widgets, real-time data refresh rate, fleet-level KPIs, and role-based data visibility not described. |  |  |  | 2026-05-04
F-054 | 9 – Fleet & Business Management | View Fleet Fuel Spend | Scope: Fleet-wide ¦ Per-vehicle | Fleet admin reviews fuel spend rolled up across the fleet and drilled down per vehicle. | Backlog | No | — | P3 | Partially Specified | #117: No fleet fuel spend dashboard. ¦ #118: No per-vehicle fuel spend. | #117: Time-period selection, export options, and how fuel spend is allocated per vehicle vs. per driver not described. ¦ #118: How fuel price is sourced (manual input, geo-based pump prices, or user preference?) and cost-per-mile calculation methodology not specified. |  |  |  | 2026-05-04
F-055 | 10 – Settings & Profile | Edit Profile Information | Fields: Name ¦ Avatar ¦ Email ¦ Mobile | User updates their profile from Settings. | Shipped to Prototype | Yes | Settings → profile row → Edit Profile | P0 | Partially Specified | #127: 'Edit Profile' + 'Tap to change photo' + 'First name' / 'Last name' / 'Email Address' / 'Mobile number' inputs + 'Save Changes' | #127: Avatar upload source (camera vs. gallery), file size limits, and image cropping UI not described. |  |  |  | 2026-05-04
F-056 | 10 – Settings & Profile | Change Account Password | — | User changes their account password from Security settings. | Shipped to Prototype | Yes | Settings → ACCOUNT & SECURITY → Change Password | P0 | Not Specified | #122: 'Change Password' + 'Current Password' / 'New Password' / 'Confirm New Password' / 'Save Password' | #122: Password change flow (current-password confirmation, strength requirements, re-login prompt after change) not described in any document. |  |  |  | 2026-05-04
F-057 | 10 – Settings & Profile | Configure Notification Preferences (Top-Level) | Categories: Speed ¦ Geofence ¦ Trip Start/End ¦ Vehicle Health | User toggles top-level notification categories from Settings (drills into F-036 / F-037 for deeper config). | Shipped to Prototype | Yes | Settings → NOTIFICATIONS section | P0 | Partially Specified | #125: Speed Alerts / Geofence Alerts / Trip Start-End / Vehicle Health rows | #125: Full set of configurable alert types, vehicle-level vs. account-level granularity, and interaction with per-geofence alert modes not fully described. |  |  |  | 2026-05-04
F-058 | 10 – Settings & Profile | Manage Vehicles (from Settings) | Action: Add new ¦ Remove ¦ Edit name/details ¦ Manage / re-pair OBD device | User manages vehicles from Settings (cross-module: also covers Fleet add/remove). | Shipped to Prototype | Partial | Settings → 'Add Vehicle' ; Settings → 'Remove Vehicle' ; Settings → vehicle row ; Settings → vehicle row → 'Re-pair' / 'Repair Device' | P1 | Partially Specified | #109: 'Add Vehicle' button in Settings; not specifically tagged 'fleet'. Fleet pricing tier exists. ¦ #114: 'Remove Vehicle' string + ' Vehicle Added' present; remove modal flow not verified. ¦ #120: 'Add Vehicle' row in Settings VEHICLES & DEVICES section ¦ #128: Vehicle row in Settings shows nickname + OBD ID; nickname-edit-from-settings flow not directly verified (verified in onboarding). ¦ #130: 'Repair Device' + 'Re-pair' + 'Connect Device' strings; full device-management screen not directly verified. ¦ #131: 'Remove Vehicle' string in bundle; removal modal not directly verified. | #109: Fleet-specific addition flow vs. onboarding addition not differentiated. Role-based access (fleet admin vs. driver) not described. ¦ #114: No removal flow, data-retention policy after removal, or reassignment of vehicle data described in any document. ¦ #120: Whether the same 6-step onboarding flow is reused or a simplified flow exists for adding subsequent vehicles not described. ¦ #128: Editable fields beyond nickname (license plate, color, icon) and save/cancel flow not fully described. ¦ #130: Device management screen content, available actions (rename, unpair, replace), and what happens to historical data after unpairing not described. ¦ #131: Data retention policy after removal, confirmation flow, and impact on active alerts / geofences for that vehicle not described. |  |  |  | 2026-05-04
F-059 | 10 – Settings & Profile | Manage Subscription Plan | Action: View plan ¦ Switch period ¦ Upgrade plan ¦ Downgrade plan ¦ Cancel ¦ Resubscribe | User manages their subscription tier and billing period from Settings. | Shipped to Prototype | Yes | Settings → 'Switch to Monthly' / 'Switch to Annual' ; Settings → Subscription block ; Settings → Subscription → 'Upgrade or change plan' / 'Switch Plan' | P1 | Partially Specified | #134: 'Switch to Monthly · $9.65/month · cancel anytime' link in Subscription block ¦ #136: 'Switch Plan' + 'Change Plan' + 'Choose a plan. You can switch again any time.' ¦ #138: 'Annual Plan · Renews Jan 15, 2026 · $7.99/mo' shown | #134: Mid-cycle upgrade proration, credit application, and billing-date change timing not described. ¦ #136: Mid-cycle proration calculation, payment confirmation UX, and feature activation timing after upgrade not described. ¦ #138: Renewal date display, plan-limit indicators (vehicle count remaining), and what happens at plan expiry not described. |  |  |  | 2026-05-04
F-060 | 10 – Settings & Profile | Manage Payment & Billing | Surface: Add / update payment method ¦ View billing history | User updates the card on file and reviews past invoices. | Shipped to Prototype | Partial | Settings → Subscription → Payment Method | P1 | Partially Specified | #121: 'Payment Method' / 'Card number' / 'Name on card' form present; mid-flow payment update not verified. ¦ #137: No billing history list visible. 'Next charge' shown but no past invoices. | #121: Supported payment types (credit card, PayPal, ACH?) and PCI-DSS handling / security indicators not specified. ¦ #137: Invoice download format, date range filter, and refund/dispute initiation not described. |  |  |  | 2026-05-04
F-061 | 10 – Settings & Profile | Configure Voice Assistant | Provider: Amazon Alexa ¦ Google Assistant | User links a voice assistant to TrackLynk for hands-free queries. | Backlog | No | — | P3 | Not Specified | #123: No Alexa integration in bundle. ¦ #124: No Google Assistant integration in bundle. | #123: Alexa skill linking flow, authorization, supported queries, and de-linking steps not described. ¦ #124: Google Action linking flow, supported query types, and de-linking steps not described. |  |  |  | 2026-05-04
F-062 | 10 – Settings & Profile | Help & Support | Surface: In-app chat ¦ Knowledge base search ¦ Submit ticket | User accesses help via chat, KB search, or ticket submission. | Shipped to Prototype | Partial | Settings → Help & Support → 'Reach Us Directly' / 'Send Message' ; Settings → Help & Support → Send Message | P2 | Partially Specified | #119: 'Send Message' form + 'Describe your issue and we'll respond to your registered email' — email-based, not live chat. ¦ #132: No knowledge-base search. Help has 'Frequently Asked' (FAQ list) and 'Send Message'; no KB search bar. ¦ #133: 'Send Message' form (issue type + description); routes to email — not a structured ticket system. | #119: Support hours, bot vs. human routing, response-time SLA, and chat transcript access not described. ¦ #132: Knowledge base access point in UI, search UX, article categories, and offline availability not described. ¦ #133: Ticket creation form fields, file attachment support, ticket status tracking UI, and expected response-time SLA not described. |  |  |  | 2026-05-04
F-063 | 10 – Settings & Profile | Privacy & Data Actions | Action: Export data ¦ Delete account | User exports a copy of their data or permanently deletes the account. | Shipped to Prototype | Yes | Settings → Delete Account → Confirm Deletion ; Settings → Privacy & Data → Export My Data | P0 | Partially Specified | #126: 'Delete Account' + 'Confirm Deletion' + 'Continue to Delete' + 'Permanently Delete Account' + 'Keep My Account' ¦ #129: 'Export My Data' + 'Export Requested' + 'Download a copy of your Tracklynk data' | #126: Confirmation steps (type 'DELETE', re-authenticate, final warning dialog), data deletion timeline, and grace-period / undo window not described. ¦ #129: Export format (CSV, JSON, PDF?), delivery method (in-app download vs. email link), processing time, and data scope not described. |  |  |  | 2026-05-04
F-064 | 10 – Settings & Profile | View Legal Documents | Document: Privacy Policy ¦ Terms of Service | User opens the privacy or terms document. | Shipped to Prototype | Yes | Settings → MORE → Terms & Privacy → Privacy Policy ; Settings → MORE → Terms & Privacy → Terms of Service | P1 | Partially Specified | #139: 'Privacy Policy' + 'Data we collect' / 'How We Use Your Data' / 'What We Collect' ¦ #140: 'Terms of Service' page in bundle | #139: Whether content opens in an in-app WebView or external browser, and whether it is accessible offline, not specified. ¦ #140: Same gap as Privacy Policy — display method and offline access not specified. |  |  |  | 2026-05-04
F-065 | 10 – Settings & Profile | Toggle Dark / Light Mode | Mode: Dark ¦ Light ¦ System | User overrides the app theme. | Backlog | No | — | P2 | Fully Specified | #135: No light-mode toggle. App appears dark-mode only. |  |  |  |  | 2026-05-04